## Summary
SUMMARY: AUTO POPULATED - DO NOT ENTER DATA HERE
| Project Name | XLC Steering Committee - Risk Register Demo
| Project Manager | Harish Darne
| Funding No. | #REF!
| Technology Deployed: | 0
Risk Matrix
| TO BE DEVELOPED |  | TO BE DEVELOPED |  |  |  | Probablity
| SUMMARY - RISK COUNT BY RATING |  | TOP 5 RISKS |  |  |  | 0.9 | 0.045 | 0.09 | 0.18 | 0.36 | 0.72
| Rating | # | Risk # | Risk ID | Risk Title | RiskExposure | 0.7 | 0.035 | 0.07 | 0.14 | 0.28 | 0.56
| HIGH (H) (Red) | 0 | Risk 1 | R001 | Supply Chain Disruption | 0.2 | 0.5 | 0.025 | 0.05 | 0.1 | 0.2 | 0.4
| MODERATE (M) (Yellow) | 0 | Risk 2 | R002 | Regulatory Approval Delays | 0.2 | 0.3 | 0.015 | 0.03 | 0.06 | 0.12 | 0.24
| LOW (L) (Green) | 0 | Risk 3 | R003 | Technology Integration Failure | 0.2 | 0.1 | 0.005 | 0.01 | 0.02 | 0.04 | 0.08
| TOTAL | 0 | Risk 4 | R008 | Environmental Non-Compliance | 0.24 |  | 0.05 | 0.1 | 0.2 | 0.4 | 0.8
|  |  | Risk 5 | R010 | Project Timeline Overrun | 0.18 |  | Impact
HIGH (H) – Unacceptable. Major disruption likely; different approach required; priority management attention required.
MODERATE (M) – Some disruption; different approach may be required; additional management attention may be needed.
LOW (L) – Minimum impact; minimum oversight needed to ensure risk remains low.

## Legend
LEGEND:
Administrative | Project Name | Enter the offical Title/Name of the Project
| Project Manager | Individual responsible for creating, updating and maintaining the integrity of the risk register. Individual assigned with the responsibility of documenting risks and orchestrating project risk updates with the risk owners.
| Funding No. | The funding number is assigned by the OFM (Office of Financial Management) once the project is approved for funding.
| Technology Deployed | Technology deployed is the category or component of a system under development in this project. The categories of technologies currently available are: Mid-tier (application), Desktop, Mainframe, Database, Infrastructure, Office Automation or Telecommunications.
Risk Identification | Risk ID | A unique identifier in a numbering system assigned to a risk. The identifier should be used for reference or for cross-reference in the future among project team members and future project stakeholders in search of historical information. Example: R01, R02, R03...
| Date Identified | The original date when the risk was originally brought to light, or identified. Example: "MM/DD/YY'
| Risk Submitter | The name of the individual or group who identified and submitted the risk to bring the attention of project stakeholders.
| Risk Title (NEW) | Short title/description of the risk - No more than 10 words
| Risk Description | A brief description of future event that could result in either positive or negative results to the project, and the impact it will have on the project.
| Source (NEW) | Source of risk. These values are list in cells in the Source Data Tab.
| Risk Owner | The risk owner is the individual assigned to the project who tracks the risks for triggers.
| Risk Type | Risks can be positive (opportunity) or negative (threat.) An example of an opportunity is "The latest UML software will reduce programming efforts by 30%, thus decreasing the amount of hours needed to produce the software." An example of a threat is "A tornado can hit the remote city of Alabama as forecasted where the software developers are." Select "Threat" or "Opportunity" as appropriate
| Risk Category | If the risk is to occur, it will come from a root source. such as: nature, lack or abundance of technology, sponsorship, communications, schedule, budget, contracts and scope. For example, "With the support of sponsors, there will be enough resources dedicated to the project." The example references a positive risk or opportunity. Select from categories as defined by the Risk Management Plan. These values are list in cells in the Source Data Tab.
| RiskTrigger - Description | Specifically what causes the risk to become a realized issue/problem - usually written in the form "If <"this" occurs>". Brief description impact (positive or negative) on the project should the risk event occur.
| Risk Trigger- Expected Date (NEW) | The estimated date on which the trigger event is expected to occur and impact the program.
| Potential Outcome (MODIFIED) | What happens if the trigger event occurs - usually written in the form "then <this outcome occurs>".
| Task ID | The task ID is the task defined in the network diagram, activity list or schedule that will be affected by the risk. As an example, "There is not enough feedback from end-to-end user testing when the codes are updated and changed. Members from the unit testing group will have the older codes, which will generate outdated and irrelevant applications in the future. The impact will be to the quality of the product in the next release." The unit testing tasks are the affected tasks, and their relevant Task IDs should be identified and documented in this case.
| Associated Risks | Associated risks are inter-related. If an event is to take place in the near future, these other events will also take place. As an example and not a fact, "If the commercial rental rates decrease in the South where the offsite contractors are, there will be an impact on the overhead costs in the facilities of New Mexico, Arizona and Georgia" which could be associated with "the future possibility that the towns of New Mexico, Arizona and Georgia will attract less skilled and efficient employees thus harnessing the outcomes of a high-tech project."
Risk Analysis | Probability Rating | Probability of risk being realized, using scales defined in the Risk Management Plan. (See Prob-Impact Matrix tab)
| Prob Value (NEW) | Numeric value of associated with the Probabiltity Rating. These values are list in cells in the Source Data Tab.
| Impact Rating | Qualitative ranking of impact to project, using scales defined in the Risk Management Plan. (See Prob-Impact Matrix tab)
| Impact Value (NEW) | Numeric value of associated with the Impact Rating. These values are list in cells in the Source Data Tab.
| Risk Exposure Score (MODIFIED) | This is calculated once you select the Impact and Probability. These cells use conditional formatting to display color shadings as defined in the Source Data Tab. . (For explanation of Impact and Probablility - See Prob-Impact Matrix tab)
| Top 5 Y/N (NEW) | Top 5 Risk notation - Enter "Y" - if risk is one of the 5 top rated risks and "N" or leave blank if it rated below the top 5 risks
Risk Mitigation Planning | Risk Response Type | Risk responses are chosen according to their risk categories. If a risk is positive or is to bear an opportunity, the risk response type could be to accept the risk, exploit the risk or enhance the risk. If a risk is negative or it is a threat, the risk response type could be to mitigate or avoid the risk. For both situations, one can chose to transfer and share the risk with a different party. Sharing or transferring a risk can be used when the resources and expertise are limited, though many other cases lend to the option for choosing these risk responses. Select from strategies as defined by the Risk Management Plan. These values are list in cells in the Source Data Tab. Select one of the following: "Accept", "Transfer", "Mitigate", "Avoid", "Share", "Exploit", "Enhance" - .
| Risk Response Description | Based upon the choice selected for "Risk Response Type," outline how you plan on responding to the risk. An example is to "Purchase software when the company's marketing news release is made public to bring the efficiency factor up by 30%."
Risk Monitoring & Control | Risk Trigger Occurance | The risk trigger occurrence communicates if the risk has or has not taken place. Select "YES" or "NO"
| Trigger Date Occurance (NEW) | If triggered, the date the trigger occurred. The risk trigger occurrence communicates if the risk has or has not taken place.
| Status | Risk status (e.g. whether it has been triggered or not). Select from one of the values listed in the drop down list. These values are list in cells in the Source Data Tab.
| Notes (NEW) | Additional notes - use as required to expand on explations or provide reminders.

## Risk Register Tool
Project Name: Building New EV Plant |  | XLC Steering Committee - Risk Register Demo |  |  |  |  | Project Manager: | Harish Darne | [7 empty] | Technology Deployed:
|  |  |  | Risk Identification | [6 empty] | Risk Analysis |  |  |  |  | Risk Mitigation Planning |  |  | Risk Tracking
Risk ID | Date Identified | Risk Submitter | Risk Title | Risk Description | Source (Select) | Risk Owner | Risk Type (Select) | Risk Category (Select) | Probability Rating (Select) | Prob Value | Impact Rating (Select) | Impact Value | Risk Exposure (Actual) | Risk Exposure | Top 5 Y/N (Select) (See Comment) | Risk Response Type (Select) | Risk Response Description | Risk Trigger Occurance (Select) | Trigger Date Occurance | Status (Select) | Notes
R001 | 2025-01-30 | Tejal Chauhan | Supply Chain Disruption | Potential delays or cost increases due to global supply chain instability affecting raw materials/components. | Formal Risk Review | Tejal Chauhan | Threat | Technical | Likely | 0.2 | Very Serious | #N/A | #N/A | #N/A | Y | Mitigate/Control | Diversify suppliers, maintain buffer inventory, negotiate flexible contracts, and monitor geopolitical conditions. | Y | 2025-02-01 | Identified | Suppliers re-evaluated monthly.
R002 | 2025-02-05 | Harish Darne | Regulatory Approval Delays | Delays in obtaining necessary environmental or zoning approvals could push back construction timelines. | Formal Risk Review | Harish Darne | Threat | Schedule | Likely | 0.2 | Very Serious | #N/A | #N/A | #N/A | Y | Mitigate/Control | Engage regulatory consultants early, track application timelines, and maintain regular communication with authorities. | Y | 2025-02-08 | Planning Complete | Monitoring permit approval status.
R003 | 2025-02-06 | Prajakta Pohare | Technology Integration Failure | Delays or failures in implementing AI, IoT, or automation systems during setup could affect plant operations. | Stakeholder | Prajakta Pohare | Threat | Technical | Likely | 0.2 | Very Serious | #N/A | #N/A | #N/A | Y | Mitigate/Control | Conduct early testing and phased rollouts, hire experienced integrators, and maintain backup systems. | Y | 2025-02-10 | Resolved | Testing scheduled in early implementation phase.
R004 | 2025-03-07 | Wasuphon Wongvilaivarin | Skilled Labor Shortage | Challenges in hiring and retaining qualified staff could impact plant readiness and early production. | Stakeholder | Wasuphon Wongvilaivarin | Threat | Communication | Near Certainty | #N/A | Significant | #N/A | #N/A | #N/A | N | Mitigate/Control | Collaborate with local technical schools, offer competitive wages, and implement workforce retention programs. | Y | 2025-03-09 | Resolved | Recruitment partnership with local institutions initiated.
R005 | 2025-03-08 | Hildah Kinoti | Budget Overruns | Unexpected increases in material or labor costs could lead to project going over budget. | Audit/Review | Hildah Kinoti | Threat | Budget | Likely | 0.2 | Serious | #N/A | #N/A | #N/A | N | Mitigate/Control | Track spending monthly, include contingency buffer in the budget, and review contracts for cost control. | Y | 2025-03-12 | Triggered | Contingency buffer of 15% in place.
R006 | 2025-03-09 | Prajakta Pohare | Production Equipment Failure | Failure of critical manufacturing equipment could halt production and delay timelines. | Stakeholder | Prajakta Pohare | Threat | Communication | Likely | 0.2 | Serious | #N/A | #N/A | #N/A | N | Mitigate/Control | Implement predictive maintenance schedules and keep essential spare parts in inventory. | Y | 2025-03-12 | Triggered | Maintenance team trained on rapid response procedures.
R007 | 2025-03-10 | Jayde Black | Quality Control Issues | Inadequate quality control may lead to defective products and brand damage. | Stakeholder | Jayde Black | Threat | Communication | Likely | 0.2 | Serious | #N/A | #N/A | #N/A | N | Mitigate/Control | Deploy AI-driven quality control systems and conduct regular audits and staff training. | Y | 2025-03-15 | Resolved | Automated inspection setup in progress.
R008 | 2025-04-11 | Cole Young | Environmental Non-Compliance | Violations in emission limits or waste disposal regulations can result in penalties or shutdown. | Stakeholder | Cole Young | Threat | Weather | Low Likelihood | #N/A | Catastrophic | #N/A | #N/A | #N/A | Y | Mitigate/Control | Use green energy systems, monitor emissions in real-time, and perform frequent internal audits. | Y | 2025-04-13 | Triggered | Real-time monitoring tools under procurement.
R009 | 2025-04-12 | Thanatat Phuangrayab | Negative Public Perception | Public backlash over environmental or labor practices may harm brand image and sales. | Stakeholder | Thanatat Phuangrayab | Threat | Scope | Low Likelihood | #N/A | Serious | #N/A | #N/A | #N/A | N | Mitigate/Control | Engage in transparent communications, showcase sustainability efforts, and respond quickly to concerns. | Y | 2025-04-16 | Triggered | Crisis communication plan in place.
R010 | 2025-04-13 | John Anderson | Project Timeline Overrun | Delays across planning, construction, or commissioning phases may extend go-live date. | Stakeholder | John Anderson | Threat | Sponsorship | Near Certainty | #N/A | Serious | #N/A | #N/A | #N/A | Y | Mitigate/Control | Use agile project tracking tools, enforce strict milestone reviews, and apply buffer time in schedule. | Y | 2025-04-18 | Planning Complete | Milestone review system implemented bi-weekly.
R011 | 2025-05-14 | Shreya Shah | Government Incentive Boost | Additional clean energy funding or tax credits may reduce project costs and improve ROI. | Stakeholder | Shreya Shah | Opportunity | Political | Highly Likely | #N/A | Serious | #N/A | #N/A | #N/A | N | Enhance | Engage policy experts to monitor and apply for incentives; maintain eligibility through compliance. | Y | 2025-05-15 | Planning Complete | Monitoring federal and state clean energy programs for eligibility.
R012 | 2025-05-15 | Nancy Green | EV Market Growth Surge | Increased consumer demand could lead to early profitability and expansion potential. | Audit/Review | Nancy Green | Opportunity | Technical | Highly Likely | #N/A | Serious | #N/A | #N/A | #N/A | N | Enhance | Scale marketing efforts, enhance brand positioning, and prepare to increase production capacity. | Y | 2025-05-15 | Planning Complete | Market trends reviewed monthly by marketing team
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
[10 empty] | #N/A |  | #N/A | #N/A | #N/A
Note on P3: THydock: To identify the TOP 5 Risk - - Filter the spreadsheet - Select the Filter Arrow button in the low right corner of the "Risk Exposure" ColumnTiitle - Select "Number Filters" - Select "Top 10" - Change "10" to "5" - Select "OK"

## Source Data Tables
Risk Source | Risk Category | LINKED |  |  | Risk Response Type | Risk Trigger Occurance
Internal Dataset | Technical | Impact Rating |  |  | Accept | Y
Stakeholder Inputs | Stategic | High | 0.6 |  | Transfer | N
Analytical Output | Organizational | Medium | 0.4 |  | Mitigate/Control
Stakeholder Review | Communication | Low | 0 |  | Avoid
Dashboard Review |  |  |  |  | Share
[5 empty] | Exploit | Status
[5 empty] | Enhance | Identified
|  | LINKED |  |  |  | Analysis Complete
|  | Probabilty Rating |  |  |  | Planning Complete
|  | Likely | 0.2 |  |  | Triggered
Risk Type |  | Possible | 0.6 |  |  | Resolved
Threat |  | Unlikely | 0.2 |  |  | Retired
Opportunity | [5 empty] | Cancelled
Not Started
|  | DO NOT REMOVE LINKED TO TOOL |  |  |  | TO BE DEVELOPED
|  | Green/Yellow/Red Threshold Values |  |  |  | Risk Count by Threshold Value
|  | Green - maximum score |  | 0.05 |  | High
|  | Yellow - minimum score |  | 0.06 |  | Medium
|  | Yellow - maximum score |  | 0.14 |  | Low
|  | Red - minimum score |  | 0.15 |  | Total
|  | White - Blank Cell |  | 0
Y/N
Y
N

## Risk Register
Risk ID | Date Identified | Risk Title | Risk Description | Source | Risk Owner | Risk Type | Risk Category | Probability | Impact | Exposure | Top 5 | Risk Response Type | Response Description | Trigger | Trigger Date | Status | Notes
R001 | 2025-05-24 | Incomplete or Dirty Data | Data has missing values or formatting issues that affect model performance | Internal Dataset | Data Analyst | Threat | Technical | Likely | High | High | Yes | Mitigate/Control | Apply imputation, outlier detection, and consistency checks | Y | 2025-05-25 | Planning Complete | Use robust data wrangling pipeline in Python
R002 | 2025-05-24 | Ambiguous Churn Definition | Definition of churn not aligned across teams, leading to inconsistent interpretation | Stakeholder Inputs | Project Manager | Threat | Strategic | Possible | Medium | Medium | No | Avoid | Align on business definition of churn in early meetings | N | N/A | Identified | Document churn rules in project charter
R003 | 2025-05-24 | Model Overfitting | Predictive model may fit training data too well and perform poorly in production | Analytical Output | Data Scientist | Threat | Technical | Possible | High | High | Yes | Mitigate/Control | Use cross-validation, regularization, and monitor live performance | N | N/A | Planning Complete | Set up monitoring dashboard
R004 | 2025-05-24 | Stakeholder Buy-In | Project findings may not be accepted by leadership or used for decisions | Stakeholder Review | PM + Analyst | Threat | Organizational | Possible | High | Medium | Yes | Share | Involve stakeholders in regular reviews and explain model logic in simple terms | Y | 2025-06-01 | Identified | Stakeholder meetings scheduled bi-weekly
R005 | 2025-05-24 | Misinterpretation of Insights | Visuals or statistics might be misunderstood leading to poor decisions | Dashboard Review | Analyst + PM | Threat | Communication | Unlikely | Medium | Low | No | Mitigate/Control | Add tooltips and explanations in the dashboard | N | N/A | Not Started | Prepare a visual analytics guide